## Gantt Chart Template
| PROJECT TITLE | Human Elephant Conflict Mitigation System |  |  | COMPANY NAME | [10 empty] | Deep11
| PROJECT MANAGER | Gunarakulan Gunaretnam (2208408) |  |  | DATE | [10 empty] | 09/28/2022
WBS NUMBER | TASK TITLE | START DATE | DUE DATE | DURATION | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12 | [6 empty] | WEEK 13 | [6 empty] | WEEK 14 | [6 empty] | WEEK 15 | [6 empty] | WEEK 16 | [6 empty] | WEEK 17 | [6 empty] | WEEK 18 | [6 empty] | WEEK 19 | [6 empty] | WEEK 20 | [6 empty] | WEEK 21 | [6 empty] | WEEK 22 | [6 empty] | WEEK 23 | [6 empty] | WEEK 24 | [6 empty] | WEEK 25 | [6 empty] | WEEK 26 | [6 empty] | WEEK 27 | [6 empty] | WEEK 28 | [6 empty] | WEEK 29 | [6 empty] | WEEK 30
[5 empty] | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S
1 | Project Conception and Initiation
1.1 | Conceptualize the Ideas (Brainstorm) | 2022-09-26 | 2022-09-28 | 3 | bar: WEEK 1 M to WEEK 1 W
1.2 | Read Related Research Papers | 2022-09-29 | 2022-10-02 | 4 | bar: WEEK 1 R to WEEK 1 S
1.3 | Analyze ideas and choose the best approaches | 2022-10-03 | 2022-10-05 | 3 | bar: WEEK 2 M to WEEK 2 W
1.4 | Gather System Requirements | 2022-10-06 | 2022-10-09 | 4 | bar: WEEK 2 R to WEEK 2 S
1.5 | Convert Manual Requirements as Technical Steps | 2022-10-10 | 2022-10-12 | 3 | bar: WEEK 3 M to WEEK 3 W
1.6 | Define Project Deliverables | 2022-10-13 | 2022-10-15 | 3 | bar: WEEK 3 R to WEEK 3 S
1.7 | Evaluate Aim/Objectives/Goals | 2022-10-16 | 2022-10-17 | 2 | bar: WEEK 3 S to WEEK 4 M
1.8 | Broke Down Tasks as Objectives | 2022-10-18 | 2022-10-20 | 3 | bar: WEEK 4 T to WEEK 4 R
1.9 | Define System Features | 2022-10-21 | 2022-10-23 | 3 | bar: WEEK 4 F to WEEK 4 S
1.1 | Work on the Legal Side of the Project | 2022-10-24 | 2022-10-25 | 2 | bar: WEEK 5 M to WEEK 5 T
1.11 | Define Resources | 2022-10-26 | 2022-10-27 | 2 | bar: WEEK 5 W to WEEK 5 R
1.12 | Design the Artifact | 2022-10-28 | 2022-10-29 | 2 | bar: WEEK 5 F to WEEK 5 S
1.13 | Work on UI/UX design | 2022-10-30 | 2022-10-31 | 2 | bar: WEEK 5 S to WEEK 6 M
2 | Write a Project Proposal |  |  | 0
2.1 | Write abstract | 2022-11-01 | 2022-11-01 | 1 | bar: WEEK 6 T
2.2 | Write defined features | 2022-11-02 | 2022-11-02 | 1 | bar: WEEK 6 W
2.3 | Write project description | 2022-11-03 | 2022-11-03 | 1 | bar: WEEK 6 R
2.4 | Write other topics & Formatting | 2022-11-04 | 2022-11-04 | 1 | bar: WEEK 6 F
3 | Prototype Building & Experimenting
3.1 | Start building basic prototype Elephant detection model¦ Learn Tensorflow / Machine Learning / AI ¦ Data collection | 2022-11-05 | 2022-11-15 | 7 | bar: WEEK 6 S to WEEK 8 T
3.2 | Learn OpenCV ¦ Experiment/Install Software Resources ¦ Basic Data Annotation | 2022-11-16 | 2022-11-22 | 6 | bar: WEEK 8 W to WEEK 9 T
3.3 | Learn to train object detection model | 2022-11-23 | 2022-11-25 | 3 | bar: WEEK 9 W to WEEK 9 F
3.4 | Download the dataset from Google and train a dummy model (Experiment) ¦ Train with 1000 images | 2022-11-26 | 2022-11-30 | 4 | bar: WEEK 9 S to WEEK 10 W
3.5 | Project Milestones and Project Aim/Objectives/Goals | 2022-12-01 | 2022-12-02 | 2 | bar: WEEK 10 R to WEEK 10 F
3.6 | Work on System Design ¦ Add extra feature | 2022-12-03 | 2022-12-05 | 3 | bar: WEEK 10 S to WEEK 11 M
3.7 | Work on Contextual Report
3.8 | Write documents | 2022-12-06 | 2022-12-06 | 1 | bar: WEEK 11 T
3.9 | Literature Review formatting documenting | 2022-12-07 | 2022-12-08 | 2 | bar: WEEK 11 W to WEEK 11 R
3.1 | Diagram drawing & Full document formatting | 2022-12-09 | 2022-12-12 | 4 | bar: WEEK 11 F to WEEK 12 M
4 | Data Collection (Offline) ¦ Interview rural area farmer & people
4.1 | Vist zoos to colect data (Offline) | 2022-12-13 | 2022-12-13 | 1 | bar: WEEK 12 T
4.2 | Interview Farmer | 2022-12-14 | 2022-12-14 | bar: WEEK 12 W
4.3 | Interview rural are people | 2022-12-15 | 2022-12-15 | bar: WEEK 12 R
5 | Build an AI model for daytime detection
5.1 | Collect more daytime elephant images (Online) | 2022-12-16 | 2022-12-18 | 3 | bar: WEEK 12 F to WEEK 12 S
5.2 | Label / annotate images | 2022-12-19 | 2022-12-21 | 3 | bar: WEEK 13 M to WEEK 13 W
5.3 | Cleanup image data | 2022-12-22 | 2022-12-22 | 1 | bar: WEEK 13 R
5.4 | Prepare dataset | 2022-12-23 | 2022-12-25 | 3 | bar: WEEK 13 F to WEEK 13 S
5.5 | Write a Python script to build the model with TensorFlow | 2022-12-26 | 2022-12-30 | 5 | bar: WEEK 14 M to WEEK 14 F
5.6 | Train the model (AI Brain) | 2022-12-31 | 2023-01-04 | 5 | bar: WEEK 14 S to WEEK 15 W
5.7 | Fine-tune the daytime model | 2023-01-05 | 2023-01-06 | 2 | bar: WEEK 15 R to WEEK 15 F
5.8 | Test the daytime model | 2023-01-07 | 2023-01-07 | 1 | bar: WEEK 15 S
6 | Build an AI model for nighttime detection
6.1 | Collect more nighttime elephant images (Online) | 2023-01-08 | 2023-01-09 | 2 | bar: WEEK 15 S to WEEK 16 M
6.2 | Label / annotate images | 2023-01-10 | 2023-01-10 | 1 | bar: WEEK 16 T
6.3 | Cleanup image data | 2023-01-11 | 2023-01-11 | 1 | bar: WEEK 16 W
6.4 | Prepare dataset | 2023-01-12 | 2023-01-13 | 2 | bar: WEEK 16 R to WEEK 16 F
6.5 | Write a Python script to build the model with TensorFlow | 2023-01-14 | 2023-01-16 | 3 | bar: WEEK 16 S to WEEK 17 M
6.6 | Train the model (AI Brain) | 2023-01-17 | 2023-01-18 | 2 | WEEK 1 M: -44296
6.7 | Fine-tune the nighttime model | 2023-01-19 | 2023-01-20 | 2 | bar: WEEK 17 R to WEEK 17 F
6.8 | Test the nighttime model | 2023-01-21 | 2023-01-21 | 1 | bar: WEEK 17 S
7 | Build a monitoring system in Python (Main System)
7.1 | Write a Python script to inference the trained models | 2023-01-22 | 2023-01-26 | 5 | bar: WEEK 17 S to WEEK 18 R
7.2 | Implement OpenCV to process the videos (Input) | 2023-01-27 | 2023-01-28 | 2 | bar: WEEK 18 F to WEEK 18 S
7.3 | Write logic to break videos into frames | 2023-01-29 | 2023-01-30 | 2 | bar: WEEK 18 S to WEEK 19 M
7.4 | Process frames with the trained models to look for elephants from the video input. | 2023-01-31 | 2023-02-02 | 3 | bar: WEEK 19 T to WEEK 19 R
7.5 | Write logic to send SMS/Emails as early warning messages to the nearest villages based on the GPS location. | 2023-02-02 | 2023-02-04 | 3 | bar: WEEK 19 F to WEEK 19 S
7.6 | Write logic to play artificial sounds of buzzing bees and monkeys to block (scare) the elephants | 2023-02-05 | 2023-02-07 | 3 | bar: WEEK 20 M to WEEK 20 W
7.7 | Write a logic to update the database if elephants are found with time/date. | 2023-02-08 | 2023-02-11 | 3 | bar: WEEK 20 R to WEEK 20 S
7.8 | Write logic to automatically swap AI models depending on the day/nighttime; during the nighttime, the nighttime AI model (AI Brain) will be working, like that during the daytime, the daytime AI model (AI brain) will be working. | 2023-02-11 | 2023-02-15 | 4 | bar: WEEK 20 S to WEEK 21 W
7.8 | Write logic to run all processes in a looping manner. | 2023-02-16 | 2023-02-17 | 2 | bar: WEEK 21 R to WEEK 21 F
7.9 | Work on reflective report & Clean up ¦ Document | 2023-02-18 | 2023-02-20 | 3 | bar: WEEK 21 S to WEEK 22 M
8.1 | Build a web panel (Management System)
8.1 | Design the web panel (UI/UX) | 2023-02-21 | 2023-02-22 | 2 | bar: WEEK 22 T to WEEK 22 W
8.1 | Create the web panel with MERN Stack. | 2023-02-23 | 2023-02-26 | 4 | bar: WEEK 22 R to WEEK 22 S
8.1 | Create database | 2023-02-27 | 2023-02-27 | 1 | bar: WEEK 23 M
8.1 | Create dashboard | 2023-02-28 | 2023-03-01 | 2 | bar: WEEK 23 T to WEEK 23 W
8.1 | Create data storing budgets | 2023-03-02 | 2023-03-03 | 2 | bar: WEEK 23 R to WEEK 23 F
8.1 | Connect the monitoring system’s (Main System) database with this web panel to view information on elephant discovery. | 2023-03-04 | 2023-03-11 | 2 | bar: WEEK 23 S to WEEK 24 S
9.1 | Testing the functionalities
9.2 | Test daytime AI model accuracy. | 2023-03-12 | 2023-03-13 | 2 | bar: WEEK 24 S to WEEK 25 M
9.3 | Test nighttime AI model accuracy. | 2023-03-14 | 2023-03-14 | 0.5 | bar: WEEK 25 T
9.4 | Test the main system functionalities (Monitoring System). | 2023-03-15 | 2023-03-15 | 0.5 | bar: WEEK 25 W
9.5 | Test the web panel functionalities. | 2023-03-16 | 2023-03-16 | 0.5 | bar: WEEK 25 R
9.6 | Cleanup ¦ Format Final Report Writing | 2023-03-17 | 2023-04-23 | 18