## Gantt Chart Template
| PROJECT TITLE | Human Elephant Conflict Mitigation System |  |  | COMPANY NAME | [10 empty] | Deep11
| PROJECT MANAGER | Gunarakulan Gunaretnam (2208408) |  |  | DATE | [10 empty] | 09/28/2022
WBS NUMBER | TASK TITLE | START DATE | DUE DATE | DURATION | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12 | [6 empty] | WEEK 13 | [6 empty] | WEEK 14 | [6 empty] | WEEK 15 | [6 empty] | WEEK 16 | [6 empty] | WEEK 17 | [6 empty] | WEEK 18 | [6 empty] | WEEK 19 | [6 empty] | WEEK 20 | [6 empty] | WEEK 21 | [6 empty] | WEEK 22 | [6 empty] | WEEK 23 | [6 empty] | WEEK 24
[5 empty] | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S
1 | Project Conception and Initiation
1.1 | Project Charter | 2018-03-12 | 2018-03-15 | 3 | bar: WEEK 1 F to WEEK 1 S; WEEK 2 F to WEEK 2 S; WEEK 3 F to WEEK 3 S; WEEK 4 F to WEEK 4 S; WEEK 5 F to WEEK 5 S; WEEK 6 F to WEEK 6 S; WEEK 7 F to WEEK 7 S; WEEK 8 F to WEEK 8 S; WEEK 9 F to WEEK 9 S; WEEK 10 F to WEEK 10 S; WEEK 11 F to WEEK 11 S; WEEK 12 F to WEEK 12 S; WEEK 13 F to WEEK 13 S; WEEK 14 F to WEEK 14 S; WEEK 15 F to WEEK 15 S; WEEK 16 F to WEEK 16 S; WEEK 17 F to WEEK 17 S; WEEK 18 F to WEEK 18 S; WEEK 19 F to WEEK 19 S; WEEK 20 F to WEEK 20 S; WEEK 21 F to WEEK 21 S; WEEK 22 F to WEEK 22 S; WEEK 23 F to WEEK 23 S; WEEK 24 F to WEEK 24 S
1.1.1 | Project Charter Revisions | 2018-03-15 | 2018-03-16 | 1
1.2 | Research | 2018-03-15 | 2018-03-21 | 6
1.3 | Projections | 2018-03-16 | 2018-03-22 | 6
1.4 | Stakeholders | 2018-03-18 | 2018-03-22 | 4
1.5 | Guidelines | 2018-03-19 | 2018-03-22 | 3
1.6 | Project Initiation | 2018-03-23 | 2018-03-23 | 0
2 | Project Definition and Planning
2.1 | Scope & Goal Setting | 2018-03-24 | 2018-03-28 | 4
2.2 | Budget | 2018-03-29 | 2018-04-02 | 3
2.3 | Communication Plan |  |  | 0
2.4 | Risk Management |  |  | 0
3 | Project Launch & Execution
3.1 | Status & Tracking |  |  | 0
3.2 | KPIs |  |  | 0
3.2.1 | Monitoring |  |  | 0
3.2.2 | Forecasts |  |  | 0
3.3 | Project Updates |  |  | 0
3.3.1 | Chart Updates |  |  | 0
4 | Project Performance/Monitoring
4.1 | Project Objectives |  |  | 0
4.2 | Quality Deliverables |  |  | 0
4.3 | Effort & Cost Tracking |  |  | 0
4.4 | Project Performance |  |  | 0